STATEMENT OF WORK E-Commerce Platform — Full-Stack Development Tata CLiQ Replica ¦ Multi-Category Retail Marketplace ───────────────────────────────────── Document Version: v1.0 — Initial Release Prepared Date: May 2026 Prepared By: Senior Solutions Architect — E-Commerce Division Project Code: ECM-TCLIQ-2026-001 Document Status: FINAL — Approved for Development Classification: CONFIDENTIAL — Internal Use Only ─────────────────────────────────────

# Document Control

## Revision History

| Ver. | Date | Description | Author |
| --- | --- | --- | --- |
| 1.0 | May 2026 | Initial SOW — all sections authored | Lead Architect / PM |
| 1.1 | TBD | Client review comments incorporated | Tech Lead |
| 2.0 | TBD | Final client sign-off version | All Stakeholders |

# Table of Contents

1.  Executive Summary	3

2.  Scope of Work	4

3.  Functional Requirements	5

4.  Non-Functional Requirements	9

5.  Technical Architecture	10

6.  UI/UX & Responsive Design	12

7.  Project Timeline & Milestones	13

8.  Team Structure & Resource Plan	15

9.  Deliverables & Acceptance Criteria	16

10.  Commercial Terms	17

11.  Risk Register	19

12.  Approvals & Sign-off	20

# 1. Executive Summary

This Statement of Work (SOW) defines the complete scope, architecture, feature set, deliverables, timeline, resource plan, and commercial terms for the development of a full-featured e-commerce platform modelled on Tata CLiQ (tatacliq.com). The platform shall replicate the core user experience, product discovery flows, checkout journeys, and backend operations of the reference site, built on a modern, scalable, and maintainable technology stack.

The platform will serve as a multi-category online retail marketplace supporting Fashion, Electronics, Luxury Goods, and Home categories. It will be architected for high availability, mobile-first responsiveness, and seamless third-party integrations including payment gateways, logistics providers, and analytics platforms.

## 1.1 Project Objectives

- Deliver a feature-complete e-commerce clone matching Tata CLiQ functionality and UX

- Implement fully responsive design: Desktop (1280px+), Tablet (768px+), Mobile (320px+)

- Achieve sub-2.5-second LCP on mid-range mobile devices under 4G conditions

- Support 10,000 concurrent users at launch; horizontally scalable to 100,000+

- Achieve PCI-DSS Level 1 compliance for all payment data handling flows

- Deliver full API documentation, 80%+ test coverage, and automated CI/CD pipelines

## 1.2 Reference Platform Analysis

Tata CLiQ is a premium e-commerce marketplace owned by Tata Group, offering authentic branded products across multiple verticals. The following capabilities form the functional baseline for this SOW:

- Multi-brand, multi-category product catalog with rich filtering and faceted search

- Full authenticated user journey: Registration, OTP login, Social login, Profile management

- Advanced product pages with zoom images, size guides, and pincode-based delivery estimates

- Cart, Guest Checkout, and complete Order Management lifecycle with tracking

- Multiple payment methods: Cards, UPI, Net Banking, EMI, Wallets, BNPL, COD

- Loyalty program (CLiQ Cash reward points) — earn, redeem, expire

- Seller/Brand portal for inventory management and order fulfilment

- Admin CMS for banners, promotions, catalog management, and reporting

# 2. Scope of Work

## 2.1 In-Scope Deliverables

| Module / Component | Description | Phase |
| --- | --- | --- |
| Frontend Application | Next.js 14 SSR, all pages, responsive layout, PWA | Phase 1–2 |
| Backend API Services | Node.js microservices: Auth, Catalog, Cart, Orders, Payments | Phase 1–2 |
| Database Layer | PostgreSQL (relational), MongoDB (catalog), Redis (cache) | Phase 1 |
| Search Engine | Elasticsearch — full-text, faceted, autocomplete, fuzzy | Phase 2 |
| Admin Panel / CMS | React dashboard — catalog, orders, users, promotions, reports | Phase 3 |
| Seller / Brand Portal | Multi-tenant portal — listings, inventory, payouts, analytics | Phase 3 |
| Payment Integration | Razorpay + PayU — Cards, UPI, Wallets, EMI, BNPL, refunds | Phase 2 |
| Logistics Integration | Shiprocket / Delhivery — AWB, tracking, NDR management | Phase 2 |
| Notification Service | Email (SES), SMS (MSG91), Push (FCM), WhatsApp | Phase 2 |
| Analytics & Tracking | Google Analytics 4, Meta Pixel, Mixpanel event tracking | Phase 3 |
| DevOps & Infrastructure | AWS ECS/Fargate, CloudFront CDN, RDS, CI/CD (GitHub Actions) | Phase 3 |
| QA & Testing | Unit, Integration, E2E (Playwright), Load (k6), Security (OWASP) | All Phases |

## 2.2 Out-of-Scope Items

- Native iOS / Android mobile applications (PWA is in-scope)

- Physical warehouse management systems or ERP integration

- Custom payment gateway development (third-party APIs only)

- Product content creation — photography, descriptions, or copywriting

- Seller recruitment, business development, or partner onboarding activities

- Post-go-live support beyond the 90-day hypercare window (separate retainer)

# 3. Functional Requirements

## 3.1 User Authentication & Account Management

### 3.1.1 Registration & Login

- Mobile OTP registration (primary) + Email fallback registration flow

- Social login: Google OAuth 2.0, Facebook Login, Apple Sign-In

- JWT-based session management with secure refresh token rotation

- Multi-device session list with individual remote logout capability

- Account merging when same email/phone found across social providers

### 3.1.2 User Profile & Dashboard

- Profile management: display name, avatar upload, gender, DOB, anniversary

- Address book: multiple saved addresses with Google Maps Places autocomplete

- Order history: filterable by status, date range, category, search

- Wishlist: multi-list creation, share wishlist link, move item to cart

- CLiQ Cash wallet: live balance, transaction history, expiry display

- Notification preferences: per-channel (Email/SMS/Push/WhatsApp) per event type

## 3.2 Homepage & Navigation

- Dynamic hero carousel with CMS-managed slides, auto-play, and swipe support

- Mega-menu navigation: Categories, Brands, Offers, Luxury section, Sale pages

- Personalised feeds: Recently Viewed, Recommended For You, Trending Now

- Category banners, brand spotlights, flash sale modules with countdown timers

- Sticky header with live search bar, cart count badge, wishlist count, profile menu

- Footer: navigational links, app download CTAs, social icons, newsletter signup

## 3.3 Product Catalog & Discovery

### 3.3.1 Category & Listing Pages (PLP)

- Faceted filtering: Price range, Brand, Size, Colour, Rating, Discount %, Material, Gender

- Sort options: Popularity, Price (asc/desc), Newest Arrivals, Discount, Customer Rating

- Infinite scroll and paginated view toggle; grid and list view switcher

- Quick-view modal — add to cart or wishlist without full page navigation

- SEO-friendly URL slugs per category path; dynamic breadcrumb trail

- Applied filter chips with individual removal and clear-all option

### 3.3.2 Product Detail Page (PDP)

- Multi-image gallery with pinch-zoom, 360-degree spin viewer, and video support

- Variant selector: Size and Colour with real-time out-of-stock states per variant

- Live inventory display with low-stock urgency messaging (e.g., Only 3 left)

- Size guide modal with brand-specific size charts (cm and inches)

- Pincode-based delivery estimate, COD eligibility, and expected delivery date

- EMI calculator: bank-wise, tenure-wise breakdown with no-cost EMI highlight

- Brand information section, authenticity guarantee badge, seller rating

- Structured product description, specifications table, care instructions

- Ratings and Reviews: star breakdown, verified-purchase badge, photo reviews, Q&A

- Related sections: Similar Products, Complete the Look, Frequently Bought Together

## 3.4 Search Engine

- Autocomplete dropdown: trending searches, category suggestions, brand links

- Full-text search via Elasticsearch: fuzzy matching, synonym support, typo tolerance

- Search results page with identical facets and sort options as category listing

- Voice search support via Web Speech API on compatible mobile browsers

- Zero-results fallback: curated recommendations and popular category links

- Search analytics: click-through rate, conversion rate, abandonment tracking

## 3.5 Cart & Checkout

### 3.5.1 Cart Management

- Persistent cart synced across all devices for logged-in users

- Guest cart with automatic merge on subsequent login (no item loss)

- Quantity increment/decrement controls, item removal, Save for Later

- Real-time price recalculation; out-of-stock flagging with remove prompt

- Coupon and promo code application with clear inline error messages

- CLiQ Cash and loyalty point partial redemption with slider control

- Cart summary: MRP total, total discount, delivery charges, tax, net payable

### 3.5.2 Checkout Flow

- Single-page checkout with clearly delineated Address, Delivery, and Payment steps

- Auto-fill from saved address book; new address creation inline

- Payment methods: Credit/Debit Cards (3DS 2.0), UPI Collect and QR, Net Banking (all major banks), Wallets (Paytm, PhonePe, Amazon Pay), EMI (no-cost and standard), COD, BNPL (Simpl, LazyPay)

- Order review and summary screen before final payment confirmation

- Post-payment: confirmation page, transactional email, SMS, and push notification

## 3.6 Order Management

- Order lifecycle: Placed > Confirmed > Packed > Shipped > Out for Delivery > Delivered > Completed

- Real-time shipment tracking integrated with courier partner webhooks

- Self-serve return and exchange: reason selection, item pickup scheduling

- Refund lifecycle: original payment method reversal with status notifications

- Downloadable GST invoice (PDF), in-window order cancellation

- Support ticket creation linked to specific order line items

## 3.7 Promotions & Loyalty

- Coupon engine: percentage discount, flat discount, free shipping, BXGY, category-specific

- Flash sale module with countdown timers and limited-quantity enforcement

- CLiQ Cash: earn on purchase, expiry on inactivity, burn on next order checkout

- Referral programme: unique referral codes, tiered rewards on first-order conversion

- Brand-exclusive deals, End of Season Sale pages, curated offer landing pages

## 3.8 Admin Panel — CMS & Operations

- Real-time dashboard: GMV, Orders, Revenue, Conversion Rate, AOV, new users

- Catalog management: add/edit/archive products, bulk CSV/Excel import with validation

- Banner and content management: homepage carousel, category banners, pop-up modals

- User management: view profiles, block/unblock, export user data (GDPR compliant)

- Order management: view all orders, reassign, cancel, initiate refunds, export

- Coupon and campaign management: scheduling, usage caps, segment targeting

- Reports: sales, inventory, returns rate, seller performance, search analytics

## 3.9 Seller / Brand Portal

- Seller onboarding: KYC verification, bank account, GST registration, MSME details

- Product listing: create and edit listings, image upload pipeline, variant management

- Inventory management: stock levels, low-stock email alerts, bulk stock update

- Order dashboard: accept, pack, generate shipping label, mark as shipped

- Payout dashboard: settlement schedule, transaction reports, dispute management

- Performance analytics: impressions, clicks, conversion rate, return rate, ratings

# 4. Non-Functional Requirements

| Category | Requirement | Target / Standard |
| --- | --- | --- |
| Performance | Page Load — LCP | < 2.5 seconds on 4G mobile (100ms budget per layer) |
| Performance | API Response (p95) | < 300ms under normal load; < 800ms under peak |
| Performance | Concurrent Users | 10,000 at launch; auto-scale to 100,000+ |
| Availability | Uptime SLA | 99.9% (less than 8.76 hours downtime per year) |
| Availability | RTO / RPO | Recovery Time Objective: 1hr; Recovery Point Objective: 15 min |
| Scalability | Horizontal Scaling | AWS ECS auto-scaling on CPU and memory thresholds |
| Security | Authentication | JWT RS256, refresh token rotation, MFA-ready |
| Security | Payment Compliance | PCI-DSS Level 1; tokenised card storage via gateway |
| Security | OWASP Top 10 | Full remediation required before production go-live |
| Security | Data Encryption | AES-256 at rest; TLS 1.3 for all data in transit |
| SEO | Core Web Vitals | All green: LCP < 2.5s, INP < 200ms, CLS < 0.1 |
| SEO | Rendering Strategy | SSR + ISR via Next.js for all PLP and PDP pages |
| Accessibility | Compliance Standard | WCAG 2.1 Level AA — keyboard nav, screen reader, contrast |
| Browser Support | Targets | Chrome 90+, Firefox 88+, Safari 14+, Edge 90+ |
| Mobile Support | Breakpoints | 320px, 480px, 768px, 1024px, 1280px, 1440px and above |
| Internationalisation | Initial Scope | English (India) locale; INR currency; IST timezone |

# 5. Technical Architecture

## 5.1 Technology Stack

| Layer | Technology | Purpose / Notes |
| --- | --- | --- |
| Frontend | Next.js 14 (App Router), React 18, TypeScript 5 | SSR, ISR, React Server Components, PWA |
| Styling | Tailwind CSS + shadcn/ui component library | Design tokens, theme support, dark mode ready |
| State Management | Zustand (client) + TanStack Query (server) | Optimistic updates, server-state caching |
| Backend API | Node.js 20 + Fastify (microservices) | REST APIs + Apollo GraphQL gateway |
| Primary Database | PostgreSQL 16 (AWS RDS) via Prisma ORM | Users, Orders, Payments, Inventory |
| Catalog Database | MongoDB Atlas | Flexible product schemas and variant attributes |
| Cache / Sessions | Redis 7 (AWS ElastiCache) | Sessions, rate limiting, cart, search result caching |
| Search | Elasticsearch 8 / AWS OpenSearch | Full-text, faceted filtering, autocomplete, synonyms |
| File Storage | AWS S3 + CloudFront CDN | Product images, seller assets, PDF invoices |
| Message Queue | AWS SQS + SNS | Async order events, notifications fan-out |
| Payments | Razorpay SDK + PayU (failover) | All Indian payment methods; webhook reconciliation |
| Notifications | AWS SES (email), MSG91 (SMS), FCM (push) | Transactional and marketing communications |
| Monitoring | Datadog APM + Sentry + CloudWatch | Distributed traces, error tracking, alerting |
| CI/CD | GitHub Actions → ECR → ECS Fargate | Blue/green deployments, staging gate approvals |
| Infrastructure | Terraform (IaC) | All AWS resources version-controlled and reproducible |

## 5.2 Microservices Breakdown

The backend is decomposed into independently deployable services communicating over internal VPC via REST and event bus:

- auth-service — JWT issuance, OTP, social OAuth flows, session management

- user-service — Profile, address book, wishlist, notification preferences

- catalog-service — Products, categories, brands, attributes, media upload pipeline

- search-service — Elasticsearch index management, query DSL, synonym handling

- cart-service — Persistent cart, real-time price engine, coupon validation

- order-service — Order lifecycle state machine, split shipments, cancellations

- payment-service — Gateway orchestration, webhook handling, refund reconciliation

- notification-service — Email/SMS/push/WhatsApp fan-out via SQS consumers

- seller-service — Onboarding, inventory, fulfilment, settlement payout

- admin-service — CMS APIs, reporting aggregations, operational tooling

- api-gateway — Kong/Nginx: rate limiting, auth middleware, request routing

## 5.3 Security Architecture

- All microservices deployed in private VPC subnets; only API Gateway is publicly exposed

- AWS WAF with rate limiting rules, bot detection, and IP reputation block-lists

- Secrets exclusively managed via AWS Secrets Manager — no plaintext env vars

- Database encrypted at rest (AES-256); TLS 1.3 enforced for all inter-service traffic

- RBAC with fine-grained permission scopes for Admin, Seller, Support Agent roles

- PDPB / GDPR readiness: data minimisation, right-to-erasure endpoint, audit log

# 6. UI/UX & Responsive Design Specifications

## 6.1 Design System

- Figma design system with global tokens: colours, typography, spacing, elevation

- Component library built on shadcn/ui extended with brand-specific variants

- Primary colour: Tata Navy (#1A1A6B); Accent: Brand Red (#E4002B); Neutrals defined

- Typography: Inter (sans-serif) for UI; headings at 4 modular scale ratios

- Minimum touch target size: 44x44px on mobile per WCAG 2.1 guideline 2.5.5

## 6.2 Responsive Breakpoint Strategy

| Breakpoint | Range | Layout Behaviour |
| --- | --- | --- |
| Mobile S | 320px – 479px | Single column, bottom navigation bar, stacked product cards, thumb-zone CTA placement |
| Mobile L | 480px – 767px | Single column, slight layout expansion, 2-column product grid option |
| Tablet | 768px – 1023px | Top navigation, 3-column product grid, side filter drawer, expanded PDP layout |
| Laptop | 1024px – 1279px | Full mega-menu, 4-column grid, sticky filter sidebar on PLP |
| Desktop | 1280px – 1439px | Full layout, 4-5 column grid, extended hero carousel, all panels inline |
| Wide | 1440px+ | Max-width container (1440px) centred; gutter space used for ambient elements |

## 6.3 Mobile-Specific UX Requirements

- Bottom navigation bar: Home, Categories, Search, Wishlist, Account

- Swipe gestures: product image gallery, category tab scroll, cart item actions

- Sticky add-to-cart bar on PDP replacing the standard button when scrolled past fold

- Progressive image loading with low-quality image placeholders (LQIP) and lazy load

- Offline indicator banner; PWA install prompt after 3rd session engagement

# 7. Project Timeline & Milestones

Total estimated duration: 36 weeks (approximately 9 months) from project kick-off date. Timeline assumes prompt client feedback (maximum 5 business days per review cycle) and no major scope changes post Phase 0 requirements lock.

| Phase | Schedule | Scope and Activities | Key Deliverables |
| --- | --- | --- | --- |
| Phase 0 | Weeks 1–2 | Discovery and Architecture: Requirements lock, tech stack finalisation, system design, DB schema, API contracts, cloud environment setup, design system kickoff | API Contracts, ERD, Design System Tokens |
| Phase 1 | Weeks 3–8 | Core Infrastructure and Auth: CI/CD pipelines, Terraform IaC, Auth service, User service, base Next.js scaffold, design system components, Homepage skeleton and navigation | Auth API, User API, Dev + Staging Environments |
| Phase 2 | Weeks 9–16 | Catalog, Search and Cart: Catalog service, MongoDB schema, Elasticsearch indexing, PLP with full filter/sort, PDP with all features, image CDN pipeline, Cart service, Wishlist | PLP, PDP, Search, Cart — Fully Functional on Staging |
| Phase 3 | Weeks 17–22 | Checkout, Payments and Orders: Complete checkout flow, Razorpay and PayU integration, Order service with state machine, Logistics API, Notification service, Tracking page | End-to-End Checkout and Order Flow on Staging |
| Phase 4 | Weeks 23–27 | Admin Panel and Seller Portal: Admin CMS (banners, catalog, orders, users, coupons), Seller portal (onboarding, inventory, orders, payouts), Reporting dashboards | Admin Panel and Seller Portal Live on Staging |
| Phase 5 | Weeks 28–30 | Promotions, Loyalty and Personalisation: Coupon engine, CLiQ Cash module, Referral programme, Personalised product feeds (collaborative filtering), A/B testing framework | Promotions Engine and Loyalty Module Complete |
| Phase 6 | Weeks 31–34 | QA, Performance and Security: Full regression suite, E2E automation (Playwright), Load testing (k6) at 10k concurrent, OWASP penetration test, Core Web Vitals optimisation, WCAG audit | QA Reports, VAPT Sign-off, Performance Baseline |
| Phase 7 | Weeks 35–36 | UAT, Staging and Go-Live: Client UAT on staging, dedicated bug-fix sprint, blue/green production deployment, DNS cutover, 24/7 hypercare monitoring for 2 weeks post-launch | Production Go-Live — Platform Live |

## 7.1 Key Milestones

| Milestone | Target Date | Acceptance Criteria |
| --- | --- | --- |
| Architecture and Design Signoff | End of Week 2 | All stakeholders sign off on ERD, API contracts, and design system |
| Alpha — Homepage and Auth Live | End of Week 8 | Core infrastructure and authentication complete on staging environment |
| Beta — Catalog and Search Live | End of Week 16 | Full catalog browsing, search, and product pages functional on staging |
| Gamma — Checkout and Orders Live | End of Week 22 | Complete end-to-end purchase flow working on staging with test payments |
| RC1 — All Modules Integrated | End of Week 30 | All features complete; internal QA testing commences |
| Security and Performance Signoff | End of Week 34 | Pen test findings remediated; load test target passed; WCAG audit clear |
| Production Go-Live | End of Week 36 | DNS live; hypercare monitoring active; support team briefed |

# 8. Team Structure & Resource Plan

| Role | No. | Allocation | Responsibilities |
| --- | --- | --- | --- |
| Solution Architect / Tech Lead | 1 | Full-time | System design, architecture governance, tech decisions, code review |
| Senior Full-Stack Engineers | 3 | Full-time | Frontend (Next.js), Backend (Node.js), API and integration development |
| Frontend Engineers (React / Next.js) | 2 | Full-time | UI components, responsive design, performance optimisation, animations |
| Backend Engineers (Node.js / DB) | 2 | Full-time | Microservices, database design, third-party integrations |
| UI/UX Designer | 1 | Full-time | Figma designs, design system, component specs, UX research and testing |
| DevOps / Platform Engineer | 1 | Full-time | AWS infrastructure, Terraform, CI/CD pipelines, monitoring and alerting |
| QA / SDET Engineers | 2 | Full-time | Test automation, E2E tests (Playwright), load testing (k6), regression |
| Data / Search Engineer | 1 | Full-time | Elasticsearch, analytics pipeline, personalisation algorithms |
| Project Manager | 1 | Full-time | Sprint planning, client communications, risk management, reporting |
| Business Analyst | 1 | Part-time | Requirements documentation, acceptance criteria, UAT coordination |
| Security Consultant | 1 | Part-time | Penetration testing, PCI-DSS advisory, VAPT sign-off review |

## 8.1 Governance & Communication Cadence

- Daily stand-ups (15 minutes) — Engineering team; async-first via Slack for distributed members

- Weekly sprint reviews — PM, Tech Lead, and designated client stakeholders

- Bi-weekly sprint retrospectives — internal engineering team

- Monthly steering committee — executives, milestone review, risk and budget assessment

- Tool stack: Jira (issues), GitHub (code + PRs), Confluence (docs), Figma (design)

# 9. Deliverables & Acceptance Criteria

## 9.1 Technical Deliverables

- Fully functional e-commerce web application deployed to production AWS environment

- Source code in private GitHub repositories with complete, well-commented commit history

- API documentation: OpenAPI 3.0 / Swagger UI for all service endpoints

- Database schema documentation including ERD diagrams and data dictionary

- Infrastructure-as-Code (Terraform modules, environment variable templates, runbooks)

- CI/CD pipeline configuration with test gates and blue/green deployment scripts

- Monitoring dashboards (Datadog): latency, error rate, uptime SLA tracking, alert rules

- Admin panel and Seller portal as fully functional, separately deployable applications

## 9.2 Documentation Deliverables

- System Architecture Document (SAD) with component, sequence, and deployment diagrams

- API Integration Guide for payment, logistics, and notification provider configurations

- Admin User Manual: CMS operations, content publishing workflows, and reporting guide

- Seller Portal Guide: onboarding walkthrough, listing management, and payout documentation

- QA Test Reports: coverage summaries, load test results, OWASP VAPT findings and remediation

- Operations Runbook: disaster recovery procedures, scaling guide, on-call playbooks

## 9.3 Acceptance Criteria

- All P0 and P1 user stories accepted and signed off during UAT phase

- Zero open Critical or High severity bugs at the time of production go-live

- Load test: 10,000 concurrent users sustained with less than 1% error rate; API p95 under 300ms

- Core Web Vitals: all green thresholds in Google Search Console report on mobile

- PCI-DSS SAQ-D fully completed; OWASP Top 10 — no High or Critical findings outstanding

- WCAG 2.1 AA audit: zero critical accessibility violations across all primary user journeys

- Test coverage: greater than 80% for unit and integration tests; greater than 70% for E2E critical paths

# 10. Commercial Terms

## 10.1 Engagement Model

This project will be executed under a Fixed-Price and Time-and-Materials (T&M) hybrid engagement model. The core platform build covering Phases 0 through 6 is fixed-price. Phase 7 (UAT support and hypercare monitoring) is T&M with an agreed cap.

## 10.2 Payment Schedule

| Payment Milestone | % of Total | Terms and Conditions |
| --- | --- | --- |
| Contract Execution / Project Kick-off | 10% | Payable within 3 business days of signed contract |
| Phase 1 Signoff — Architecture and Auth Complete | 10% | Post milestone acceptance and written sign-off |
| Phase 2 Signoff — Catalog and Search Complete | 15% | Post milestone acceptance and written sign-off |
| Phase 3 Signoff — Checkout and Orders Complete | 20% | Post milestone acceptance and written sign-off |
| Phase 4 Signoff — Admin and Seller Portal Complete | 15% | Post milestone acceptance and written sign-off |
| Phase 5–6 Signoff — QA, Security and Performance | 15% | Post penetration test and load test acceptance |
| Production Go-Live — Final Acceptance | 15% | Post full UAT sign-off and production deployment verified |

## 10.3 Assumptions and Dependencies

- Client will provide all brand assets (logos, fonts, colour palettes) within 5 business days of kick-off

- API keys and credentials for all third-party services (Razorpay, MSG91, etc.) provided by client

- Client UAT feedback provided within 5 business days of each staging deployment per phase

- AWS account provisioned by client with IAM access granted to the development team

- All scope changes post Phase 0 requirements lock are subject to a formal Change Request process

## 10.4 Change Request Process

Any modification to agreed scope, timeline, or budget must follow this Change Request process:

- Client raises Change Request in writing with description and business justification

- Technical team assesses impact within 3 business days: effort estimate, cost delta, timeline impact

- Change Request approved by authorised representatives of both parties before any work commences

- Change Requests under 8 hours of effort may be approved via email by designated representatives

## 10.5 Intellectual Property

Upon receipt of the final payment milestone, the client shall own all custom-developed source code, designs, and documentation produced under this SOW. Open-source components remain governed by their respective licences. Third-party API integrations are subject to each provider's terms of service.

## 10.6 Warranty and Post-Go-Live Support

- 90-day hypercare period: bug fixes for P0 and P1 severity issues at no additional cost to client

- Warranty scope covers defects in delivered functionality, not new feature requests or enhancements

- Ongoing support and enhancements are available under a separately negotiated retainer agreement

- Hypercare SLA: P0 — 1-hour response, 4-hour resolution; P1 — 4-hour response, 24-hour resolution; P2 — 2 business days

# 11. Risk Register

Probability and Impact are rated as: H = High, M = Medium, L = Low

| Risk Description | Prob. | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- |
| Scope creep — uncontrolled additions post requirements lock | H | H | Strict Change Request process; Phase 0 lock; weekly scope review with PM | PM / Client |
| Third-party API instability — payment or logistics gateways | M | H | Fallback gateway (Razorpay primary, PayU fallback); retry logic; circuit breakers | Architect |
| Key resource attrition during project execution | M | H | Knowledge documentation; pair programming; cross-training; bench resources ready | PM / HR |
| Performance targets not met under load testing | M | H | Early load testing from Phase 2; CDN and caching strategy implemented from Phase 1 | DevOps |
| PCI-DSS compliance delays blocking go-live | L | H | Engage QSA auditor early; tokenise all card data via gateway (no raw PAN stored) | Security |
| Client feedback delays causing timeline drift | H | M | Contractual 5-day feedback SLA; escalation path defined; parallel workstreams planned | PM |
| Elasticsearch cluster degradation under high catalogue write load | M | M | Index design review in Phase 0; async indexing via SQS queue; dedicated ingest nodes | Search Eng. |
| Cross-browser and mobile compatibility regressions | M | M | BrowserStack automated cross-browser testing integrated in CI from Phase 1 onwards | QA |

# 12. Approvals & Sign-off

By signing below, the authorised representatives of both parties confirm their agreement to all terms, scope, timeline, team structure, deliverables, and commercial conditions set forth in this Statement of Work.

| Party | Name and Title | Signature | Date Signed |
| --- | --- | --- | --- |
| Client — Authorised Representative |  |  |  |
| Development Partner — Lead Architect |  |  |  |
| QA / Compliance Signatory |  |  |  |

This document is CONFIDENTIAL and PROPRIETARY. Unauthorised reproduction or distribution is strictly prohibited.

SOW v1.0  |  May 2026  |  Project Code: ECM-TCLIQ-2026-001